ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVES & EXPECTED OUTPUTS	2

2.1.	Overall objective	2

2.2.	 Specific Objective(s)	3

2.3.	Expected outputs to be achieved by the contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	4

5.	LOGISTICS AND TIMING	4

5.1.	Location	4

5.2.	Start date & period of implementation of tasks	4

6.	REQUIREMENTS	5

6.1.	Staff	5

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of North Macedonia

## Contracting authority

Chamber of Crafts Skopje

## Country background

North Macedonia was the first Western Balkan economy to sign a Stabilisation and Association Agreement (SAA) with the European Union in 2001, setting the way forward for an alignment with EU standards. The country applied for EU membership in 2004 and the status of EU candidate country was given a year later. Since 2009, the EU Commission has continuously recommended that the EU Council opens accession negotiations with North Macedonia. In 2020, the Council decided to open accession negotiations and these negotiations started in mid-2022 with the first intergovernmental screening meetings. The negotiations are important as the EU continues to be the biggest trading partner of North Macedonia (almost 80% of the Macedonian exports go to EU, 2021). Moreover, the recent history of EU enlargement since the early 2000s shows that it helped the new member states to catch up regarding economic development and standards of living.

Economic growth in the past two decades has been very volatile due to several external and domestic shocks including the deep political crisis in the years 2014 to 2017 and the COVID-19 pandemic. While the economy recovered faster than expected from the COVID-19 pandemic (GDP growth rate in 2021: +4 percent), the effects of Russia’s invasion in Ukraine (energy crisis, inflationary pressures) have reduced the growth momentum. The much-needed recovery of labour markets is lagging. The pandemic has further exposed the structural labour market problems from before COVID-19 and the current slowdown of global economic growth. These challenges are low labour market participation, in particular among women and youth, low job creation, inadequate earnings, and unproductive work.

According to the latest census results from 2021, the total resident population of the Republic of North Macedonia is 1,8 Mio inhabitants. The country lost almost 10 per cent of its population between 2002 and 2021 and is one of several depopulation hotspots in Eastern and Southeastern Europe mainly due to ageing of the population and continued emigration. According to the data of the State Statistical Office, in 2022, the labour force numbered 808,078 persons (59.4 per cent of them are men), of which 692,034 (58.5 per cent of them are men) were employed and 116,045 unemployed (64.8 per cent of them are men).

## Current situation in the sector

- The Republic of North Macedonia grapples with persistent challenges in youth employment and participation despite notable advancements in recent years. High unemployment rates among the youth population, particularly for women, underscore the need for comprehensive initiatives to address skills gaps and promote meaningful career opportunities. The current educational landscape, while witnessing increased participation in vocational education, falls short in recognizing and rewarding students with exceptional competencies, hindering their further career development. The inadequacies in entrepreneurial skills and support mechanisms, as highlighted by various studies, emphasise the critical necessity for tailored programs and initiatives to cultivate a robust entrepreneurial mindset among youth. Additionally, the lack of public-funded activities in social entrepreneurship and the predominant role of non-public organisations in this realm underscore the pressing need for initiatives that bridge this gap and harness the potential of social enterprises.

- Despite recent progress, North Macedonia continues to show very poor labour market outcomes, especially for the youth. Youth unemployment in North Macedonia is among the highest in the world (44 percent in North Macedonia in the first quarter (Q1) of 2018, compared to 15 percent in May 2018 in the EU), reflecting the challenges youth face to gain a foothold in the labour market. The poor labour market situation of young people is also reflected in high rates of the youth population not in education, employment or training (NEET). In 2017, the NEET rate was 24.9 percent in North Macedonia. The grim prospects for youth represent a challenge for inclusive growth and poverty reduction, as prolonged spells of unemployment and inactivity in these early years negatively affect subsequent labour market outcomes.

- Despite the significant impact of the COVID-19 pandemic on the economy, North Macedonia’s unemployment rate has continued to decrease, following a decade-long trend. It still remains at a high level, twice as high as in the European Union, although it reached its lowest point in 2022 and stood at 14.4 per cent, with youth unemployment (15–29) of 25.2 per cent. Another challenge apart from youth unemployment is youth inactivity. 73,574 young Macedonians (52 per cent female), or almost one out of five was neither in employment nor in education and training in 2022.

# OBJECTIVES & EXPECTED OUTPUTS

The project focuses on Priority 2 of the call for proposals: Socio-Economic Development, Job Creation, and Youth by supporting civil society and media organisations, emphasising socio-economic development, and youth engagement. It aims to equip young individuals with vital vocational skills, knowledge, and opportunities, fostering employment, self-employment, and social entrepreneurship. By fostering collaboration between public, private, and SCO sectors, the project targets the enhancement of Civil Society Organizations (CSOs) and Vocational Education and Training (VET) institutions, providing specialised skills for youth, including vocational, entrepreneurship, and social entrepreneurial skills. Through targeted support mechanisms, it seeks to boost youth entrepreneurship, craftsmanship, and social innovation, fostering sustainable socio-economic progress and reinforcing youth's role in broader community development efforts. Additionally, in line with the broader objectives of the Call for Proposals, the project aims to empower civil society to actively contribute to sector reforms within the EU integration context, ensuring students gain skills and competencies aligned with those in EU countries. The project aligns with numerous local and national initiatives that aim to create self-employment opportunities for young individuals. The action complements the country's official documents and strategic plans of the Ministry of Education and Science (MOES)7 and the Agency for Youth and Sports. One of the significant challenges in the country is the shortage of qualified skilled Vocational Education and Training (VET) workers. Despite efforts, a considerable number of students entering the job market from elementary schools lack essential skills. To tackle this challenge, the lead applicant, the Chamber of Crafts Skopje, collaborates with essential stakeholders like the Center for Vocational Education and Training and the Ministry of Education and Science. Proactive measures, such as organising skill-enhancing competitions for students, are being taken. However, since the school year 2019/2020, the national competitions organised by MOES have ceased, leaving only regional VET competitions available in the same occupational categories. Moreover, the project's action addresses youth unemployment. There are numerous initiatives and programs by the Employment Service Agency of North Macedonia8 (ESA of RNM) aimed at supporting unemployed young individuals. The project collaboratively works with ESA of RNM initiatives, focusing on empowering youth, particularly women, in self-employment, business startups, and overall economic well-being.

## Overall objective

The overall objective (Impact) to which this action contributes is:

to equip young individuals with vital vocational skills, knowledge, and prospects, fostering their ability to actively engage unemployment, self-employment, and social entrepreneurship pursuits.

## Specific objective(s)

The specific objective (Outcome) of this contract is as follows:

- Number of reports conducted to assess Skills Discrepancy and evaluate Social Entrepreneurship in VET Schools and CSOs, with a Focus on Crafts (1report)

## Expected outputs to be achieved by the contractor

The expected outputs of this contract are as follows:

Formulated final report from conducted research

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

The research aligns vocational school skills with labour market needs, addressing program mismatches, changing skills, and gaps in social entrepreneurship readiness. The goal is to tailor education to specific job requirements, guided by employer engagement and student aspirations.

## Risks

Insufficient data quality, limited crafts cooperation leading to a lack of real-world insights, potential obsolescence of findings due to rapid market changes.

# SCOPE OF THE WORK

## General

### Description of the assignment

The Consultant should conduct Research on Skills Discrepancy and Evaluation of Social Entrepreneurship in VET Schools and CSOs, with a Focus on Crafts.

### Geographical area to be covered

Republic of North Macedonia

### Target groups

- Vocational Education and Training (VET) Students: This includes 200 students from various VET schools across regions in North Macedonia. The focus is on specific vocational occupations such as hairdressing, beautician services, electrical engineering, mechanical professions, traffic-related roles, chemical technology, business occupations, and special needs education (with up to 20% inclusion). Additionally, 36 students will participate in national skill competitions, and 400 elementary school students will visit these competitions. Students need skill development and career opportunities. The action aims to bridge the gap between their education and the job market by providing practical skills, mentorship, and visibility.

- Unemployed Youth: This group involves 100 unemployed young individuals from varied social and ethnic backgrounds. These individuals need support to enhance their employability and self-employment prospects.

- Civil Society Organizations (CSOs): Minimum five CSOs that focus on engaging and delivering services to students in VET schools. They require capacity building, mentorship, project management exp

## Specific work

The Consultant should conduct a Research on Skills Discrepancy and Evaluation of Social Entrepreneurship in VET Schools and CSOs, with a Focus on Crafts in the Republic of North Macedonia.

The activity seeks to bridge the gap between VET school education and the practical needs in the crafts sector. This investigation evaluates the adequacy of VET programs, examining practical training, the presence of crafts and SMEs, and their alignment with educational profiles. It also assesses schools' readiness to teach social entrepreneurship as a self-employment option post-graduation.

This research aims together detailed statistical and qualitative insights to understand specific skill deficiencies among VET students. Additionally, it will address skills gaps within Civil Society Organizations (CSOs) engaged with VET schools and youth, aiming to support student development and empowerment within the VET system.

This research plays an essential role in establishing successful mechanisms and tools by enabling informed decision-making for educational institutions and policymakers, enhancing employability among VET graduates through targeted skill development, fostering collaboration between education and crafts for tailored curriculum adjustments, and serving as the foundation for policy development, thereby positioning vocational education with labour market demands in craft sector, entrepreneurship (social).

## Project management

### Responsible body

Chamber of Crafts Skopje is responsible for implementation of the project. Any issue regarding this project should be addressed to Chamber of Crafts Skopje.

### Management structure

The Contracting Authority is Chamber of Crafts Skopje and in that capacity, it is responsible to launch the service tender procedure, sign the service contract, authorize payments to the contractor and handle the financial management and control during project implementation. The day-to-day operational project implementation will be performed by the Project office – which is responsible for implementation of project.

### Facilities to be provided by the contracting authority and/or other parties

The Contracting Authority will provide all available information and will fully co-operate with the Consultant in order to achieve the best results. Technical information and access to the existing records, any useful information and/or documentation which may be relevant to the performance of the Contract will be provided upon request.

# LOGISTICS AND TIMING

## Location

Skopje

## Start date & period of implementation of tasks

The intended start date is 02.07.2024 and the period of implementation of the contract will be 3 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are defined and they must submit CVs and signed statements of exclusivity and availability.

All experts who have a crucial role in implementing the contract are referred to as key experts. The profiles of the key experts for this contract are as follows:

The Contractor(s) shall implement the contract with a one key expert, which shall be appointed by the Contractor to act as a Team Leader.

Key expert 1: Team Leader

The Team Leader will have overall responsibility for the smooth running and timely implementation of the research.

The Team Leader should have the possibility, in consultation with the Contractor, to mobilise backstopping expertise to address unforeseen problems and technical issues.

The Team Leader will supervise, coordinate, organise and oversee all administrative and logistical support, including control of the project expenses, the preparation and timely delivery of final report. The Contractor will ensure that the Team Leader is issued with sufficient powers to enable him/her to operate independently from the Contractor’s head office.

Team Leader must have the following background/experience:

Qualifications and skills

- Education at least Masters Degree Academic level, (where a university degree has been awarded on completion of four years study in a university or equivalent institution), in psychology, human resource management, quality management or similar area relevant for the assignment or equivalent relevant professional experience of 10 years above the general professional experience asked below

General professional experience

- The expert shall have at least 5 years' experience in the professional education sector(s).

Specific professional experience

- The expert shall have at least 3 years' experience in the sector(s) related to the improvement of professional education.

- Experience in the preparation of at least 3 researches, analyses, mentoring, trainings or preparation of studies and other documents in the area of the professional education.

Soft skills

- The expert will have excellent writing and editing skills.

All experts must be independent and free from conflicts of interest in the responsibilities they take on.

### Other experts, support staff & backstopping

CVs for experts other than the key experts should not be submitted in the tender but the tenderer will have to demonstrate in their offer that they have access to experts with the required profiles. The contractor shall select and hire other experts as required according to the needs. The selection procedures used by the contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the contractor.

## Facilities to be provided by the contractor

The contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in Macedonian in one original and one copy:

Draft final report of maximum 10 pages (main text, excluding annexes). This report shall be submitted no later than 15 days before the end of the period of implementation of tasks.

Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 5 days after receipt of comments on the draft final report. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

Formulated final report with findings from the conducted research.